## Cover
TEST REPORT DOCUMENT
Project Name | Family Care Digital Management |  |  | Creator | GSU26SE032 Test Team
Project Code | SU26SE032 |  |  | Issue Date | 2026-07-27
Document Code | SU26SE032_Report5_TestReport_v0.1 |  |  | Version | 0.1
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2026-07-27 | 0.1 | Initial Test Report draft | A | Create Test Report based on backend Jest result and pending FE/system integration scope. | Report5_Test Documentation.docx; Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx
Note on D10: *A: Add M: Modify D: Delete

## Test Cases
TEST CASE LIST
Project Name |  | Family Care Digital Management
Project Code |  | SU26SE032
Test Environment Setup Description |  | Backend: NestJS API, Jest, Prisma/PostgreSQL, Redis/BullMQ, mocked external providers where required. FE/System: pending until frontend build and integrated test environment are available.
No | Function Name | Sheet Name | Description
1 | Backend Unit Tests | Backend Unit Tests | Validate backend service, guard, utility, provider, and policy unit tests from the NestJS Jest suite.
2 | Authentication Account | Auth Account | Validate user registration, login, token lifecycle, email verification, password reset, and profile update through FE and API.
3 | Family Membership | Family Membership | Validate family workspace creation, invite code, join request, role management, member removal, and ownership transfer.
4 | Finance Management | Finance | Validate family finance ledger, categories, monthly finance, budget, goals, alerts, and reports.
5 | Task Reward | Tasks Rewards | Validate task categories, tasks, schedules, assignments, submissions, proofs, rewards, and disputes.
6 | SOS Location | SOS Location | Validate emergency contacts, SOS settings, alert lifecycle, live location, wearable events, and location sharing.
7 | Communication | Communication | Validate notifications, device tokens, chat conversations/messages, calendar events, and reminders.
8 | Album Media | Album Media | Validate media upload/list/detail/update/delete/restore, tags, moderation, face profiles, and face suggestions.
9 | Subscription Admin | Sub Admin | Validate subscription plans, checkout/webhook, admin dashboard, user/family/member/payment/revenue/system operations.
10 | AI Chatbot | AI Chatbot | Validate AI conversation, messages, read/write tools, action confirmation/rejection, and unavailable-provider behavior.

## Test Statistics
TEST STATISTICS
Project Name | Family Care Digital Management |  | Creator |  | GSU26SE032 Test Team
Project Code | SU26SE032 |  | Reviewer/Approver |  | Team Leader / Reviewer
Document Code | SU26SE032_Report5_TestReport_v0.1 |  | Issue Date |  |  | 2026-07-27
Notes | Backend Jest unit tests passed. FE/system integration test cases are prepared as Pending until the frontend build and integrated test environment are available.
No | Module code | Passed | Failed | Pending | N/A | Number of test cases
1 | Backend Unit Tests | 403 | 0 | 0 | 0 | 403
2 | Authentication Account | 0 | 0 | 8 | 0 | 8
3 | Family Membership | 0 | 0 | 7 | 0 | 7
4 | Finance Management | 0 | 0 | 8 | 0 | 8
5 | Task Reward | 0% | 0% | 700% | 0% | 700%
6 | SOS Location | 0 | 0 | 6 | 0 | 6
7 | Communication | 0 | 0 | 6 | 0 | 6
8 | Album Media | 0 | 0 | 8 | 0 | 8
9 | Subscription Admin | 0 | 0 | 7 | 0 | 7
10 | AI Chatbot | 0 | 0 | 5 | 0 | 5
| Sub total | 403 | 0 | 62 | 0 | 465
| Test coverage |  | 86.67 | %
| Test successful coverage |  | 100 | %

## Backend Unit Tests
Feature | Backend Unit Tests
Test requirement | Validate backend service, guard, utility, provider, and policy unit tests from the NestJS Jest suite.
Number of TCs | 403
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 403 | 0 | 0 | 0
Round 2 | 0 | 0 | 0 | 403
Round 3 | 0 | 0 | 0 | 403
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
TR-UT-001 | Execute backend Jest unit tests for module: admin (11 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for admin pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | Detailed cases are maintained in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
TR-UT-002 | Execute backend Jest unit tests for module: ai-chatbot (25 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for ai-chatbot pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | Detailed cases are maintained in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
TR-UT-003 | Execute backend Jest unit tests for module: albums (130 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for albums pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | Detailed cases are maintained in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
TR-UT-004 | Execute backend Jest unit tests for module: auth (34 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for auth pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | Detailed cases are maintained in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
TR-UT-005 | Execute backend Jest unit tests for module: common (11 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for common pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | This sheet summarizes Jest results by module; detailed unit cases are in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
TR-UT-006 | Execute backend Jest unit tests for module: devices (2 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for devices pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | Detailed cases are maintained in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
TR-UT-007 | Execute backend Jest unit tests for module: families (22 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for families pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | Detailed cases are maintained in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
TR-UT-008 | Execute backend Jest unit tests for module: family-members (1 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for family-members pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | Detailed cases are maintained in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
TR-UT-009 | Execute backend Jest unit tests for module: finance (59 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for finance pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | Detailed cases are maintained in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
TR-UT-010 | Execute backend Jest unit tests for module: join-requests (25 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for join-requests pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | Detailed cases are maintained in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
TR-UT-011 | Execute backend Jest unit tests for module: locations (7 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for locations pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | Detailed cases are maintained in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
TR-UT-012 | Execute backend Jest unit tests for module: notifications (28 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for notifications pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | Detailed cases are maintained in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
TR-UT-013 | Execute backend Jest unit tests for module: sos (40 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for sos pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | Detailed cases are maintained in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
TR-UT-014 | Execute backend Jest unit tests for module: tasks (8 assertions). | Run npm.cmd run test -- --runInBand --json --outputFile=../outputs/report5/jest-results.json from the server directory. | All Jest assertions for tasks pass; no failed suite or failed test is reported. | Dependencies are installed; Jest environment uses mocks or configured test providers as defined in each spec file. | Passed | 2026-07-27 | Automated Test Runner | N/A |  |  | N/A |  |  | Detailed cases are maintained in Report5_Unit_Test_FamilyCare_Draft_v0.2.xlsx.
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Auth Account
Feature | Authentication Account
Test requirement | Validate user registration, login, token lifecycle, email verification, password reset, and profile update through FE and API.
Number of TCs | 8
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 0 | 0 | 8 | 0
Round 2 | 0 | 0 | 0 | 8
Round 3 | 0 | 0 | 0 | 8
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
TR-AUTH-001 | Register new account with valid email/password | Open register screen; input valid data; submit; verify API response and email verification state. | Account is created; response envelope is successful; verification flow is available. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-AUTH-002 | Reject duplicate email registration | Submit registration with an email that already exists. | System displays validation/business error and does not create a duplicate account. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-AUTH-003 | Login with valid credentials | Input valid email/password and submit login. | Access token and refresh token are returned; user profile can be loaded. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-AUTH-004 | Reject invalid password login | Input existing email with wrong password. | System returns unauthorized error without exposing sensitive reason. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-AUTH-005 | Refresh access token | Use a valid refresh token to request new access token. | New access token is issued and old/invalid refresh token is rejected when appropriate. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-AUTH-006 | Logout current session | Call logout with current refresh token/session. | Refresh token is revoked; protected APIs require a valid token. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-AUTH-007 | Verify email by OTP | Submit valid verification OTP. | Account verification status changes to VERIFIED. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-AUTH-008 | Reset forgotten password | Request reset OTP, submit valid OTP and new password, then login again. | Password is updated and old password is no longer accepted. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Family Membership
Feature | Family Membership
Test requirement | Validate family workspace creation, invite code, join request, role management, member removal, and ownership transfer.
Number of TCs | 7
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 0 | 0 | 7 | 0
Round 2 | 0 | 0 | 0 | 7
Round 3 | 0 | 0 | 0 | 7
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
TR-FAM-001 | Create family workspace | Login as normal user and create a family with valid name/description. | Family is created and creator becomes FAMILY_MANAGER. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-FAM-002 | List my families | Call my families endpoint after creating/joining family. | Only families belonging to current user are returned. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-FAM-003 | Generate invite code | Manager regenerates invite code. | Invite code is created with valid format and stored for the family. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-FAM-004 | Create join request by invite code | Another user enters invite code and submits join request. | Join request is created with PENDING status. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-FAM-005 | Approve join request | Family manager approves pending request. | User becomes active family member and request status becomes APPROVED. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-FAM-006 | Update member role | Manager updates member role to deputy/member. | Role is updated while business limits are respected. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-FAM-007 | Remove member / transfer ownership | Manager removes member or transfers ownership to eligible member. | Membership/ownership state is updated correctly and permissions follow new role. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Finance
Feature | Finance Management
Test requirement | Validate family finance ledger, categories, monthly finance, budget, goals, alerts, and reports.
Number of TCs | 8
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 0 | 0 | 8 | 0
Round 2 | 0 | 0 | 0 | 8
Round 3 | 0 | 0 | 0 | 8
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
TR-FIN-001 | Create finance category | Manager creates an income/expense category. | Category appears in family finance category list. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-FIN-002 | Create monthly finance record | Member submits expected/actual income and expense for a month. | Monthly finance record is created and visibility rules are applied. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-FIN-003 | Update monthly finance record | Member updates current month finance values. | Existing record is updated without duplicate period row. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-FIN-004 | Create ledger entry | Manager/deputy creates shared ledger income/expense entry. | Entry is stored with correct type, amount, category, and creator. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-FIN-005 | Create and activate budget plan | Manager creates budget plan and activates it. | Plan status changes to ACTIVE and lines are available for reporting. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-FIN-006 | Create financial goal | Manager creates goal with target amount and due date. | Goal is ACTIVE and progress endpoint returns expected baseline. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-FIN-007 | Recompute budget alerts | Trigger alert recomputation after ledger/budget data changes. | Expected alerts are created/updated with correct severity/status. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-FIN-008 | View finance report summary | Open finance report/overview endpoints. | Summary values match ledger, budget, goal, and contribution data. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Tasks Rewards
Feature | Task Reward
Test requirement | Validate task categories, tasks, schedules, assignments, submissions, proofs, rewards, and disputes.
Number of TCs | 7
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 0 | 0 | 7 | 0
Round 2 | 0 | 0 | 0 | 7
Round 3 | 0 | 0 | 0 | 7
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
TR-TASK-001 | Create task category | Manager creates task category. | Category is visible in active category list. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-TASK-002 | Create ad-hoc task | Manager creates a one-time task with valid payload. | Task is created with ACTIVE or configured status. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-TASK-003 | Assign task to member | Manager assigns task to a family member. | Assignment is created and assignee can view it. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-TASK-004 | Submit task proof | Assignee submits proof/note/file for assignment. | Submission is created and proof metadata is returned. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-TASK-005 | Review task submission | Manager approves or rejects submitted task. | Submission and assignment statuses update correctly. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-TASK-006 | Create reward settlement | Reward settlement is created after approved task. | Settlement is pending/settled according to reward workflow. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-TASK-007 | Handle unavailability/dispute | Member reports unavailable or disputes reward; manager resolves. | Lifecycle status changes correctly and notifications are triggered where configured. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## SOS Location
Feature | SOS Location
Test requirement | Validate emergency contacts, SOS settings, alert lifecycle, live location, wearable events, and location sharing.
Number of TCs | 6
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 0 | 0 | 6 | 0
Round 2 | 0 | 0 | 0 | 6
Round 3 | 0 | 0 | 0 | 6
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
TR-SOS-001 | Configure SOS settings | Manager/member opens and updates SOS settings. | Settings are created/defaulted and updated values persist. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-SOS-002 | Manage emergency contacts | Add, edit, delete emergency contacts. | Contacts are ordered and visible according to family membership. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-SOS-003 | Create SOS alert | Member triggers SOS alert from app. | Alert is created with ACTIVE status and family notification is dispatched. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-SOS-004 | Push current/batch locations | Send location updates for an active alert. | Latest and historical SOS locations are stored and retrievable. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-SOS-005 | Respond and resolve SOS alert | Family member responds; manager/resolver closes alert. | Response and resolved status are stored. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-SOS-006 | Register wearable sensor event | Pair wearable and submit sensor event. | Device/event is accepted or rejected according to pairing state. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Communication
Feature | Communication
Test requirement | Validate notifications, device tokens, chat conversations/messages, calendar events, and reminders.
Number of TCs | 6
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 0 | 0 | 6 | 0
Round 2 | 0 | 0 | 0 | 6
Round 3 | 0 | 0 | 0 | 6
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
TR-COM-001 | Register and remove device token | Register FCM token then remove it. | Token ownership and deletion behavior are correct. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-COM-002 | List and read notifications | Open notification list, mark one/read-all, view unread count. | Read state and unread count update correctly. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-COM-003 | Create chat conversation | Create family chat conversation with participants. | Conversation and participant records are created. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-COM-004 | Send/edit/react/pin message | Send a chat message and perform supported message actions. | Message lifecycle and reaction/pin states update correctly. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-COM-005 | Create calendar event | Create event with participants and reminders. | Event is listed and participants receive invitation status. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-COM-006 | Respond to calendar event | Participant accepts/declines and toggles reminder. | Response status and reminder flag are updated. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Album Media
Feature | Album Media
Test requirement | Validate media upload/list/detail/update/delete/restore, tags, moderation, face profiles, and face suggestions.
Number of TCs | 8
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 0 | 0 | 8 | 0
Round 2 | 0 | 0 | 0 | 8
Round 3 | 0 | 0 | 0 | 8
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
TR-ALB-001 | Upload album media | Upload supported image/video file. | Media record is created with storage metadata and moderation status. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-ALB-002 | Reject invalid media upload | Upload unsupported type or oversized file. | Validation error is returned and no media record is created. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-ALB-003 | List and view media detail | Open album list and detail by media id. | Visibility and moderation rules are enforced. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-ALB-004 | Update/delete/restore media | Owner/manager updates metadata, soft deletes, restores, or permanently deletes. | Lifecycle fields and cleanup jobs are updated correctly. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-ALB-005 | Tag family member in media | Add/remove member tag on safe media. | Tag is created/removed only when access policy allows it. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-ALB-006 | Review moderation result | Manager reviews flagged/need-review media. | Moderation status changes according to action. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-ALB-007 | Enroll face profile | Enroll/validate/enable/disable/delete member face profile. | Consent/profile state and encrypted embedding behavior are correct. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-ALB-008 | Run face scan suggestions | Request face scan and confirm/reject suggestions. | Scan job and tag suggestion lifecycle is correct. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Sub Admin
Feature | Subscription Admin
Test requirement | Validate subscription plans, checkout/webhook, admin dashboard, user/family/member/payment/revenue/system operations.
Number of TCs | 7
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 0 | 0 | 7 | 0
Round 2 | 0 | 0 | 0 | 7
Round 3 | 0 | 0 | 0 | 7
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
TR-ADM-001 | List public subscription plans | Open subscription plans endpoint. | Active/public plans are returned with feature map. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-ADM-002 | Create family checkout session | Family manager starts subscription checkout. | Stripe checkout session is created in test mode. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-ADM-003 | Handle Stripe webhook | Send signed checkout/subscription/payment webhook. | Subscription/payment state is updated idempotently. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-ADM-004 | Admin dashboard summary | System admin opens dashboard summary. | Aggregated users/families/revenue/status metrics are returned. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-ADM-005 | Admin manage users | Admin lists, updates, locks/unlocks/deletes normal users. | Audit log is created and self/admin-protection rules are enforced. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-ADM-006 | Admin manage families/members | Admin lists and updates family/member records. | Changes follow admin permissions and audit logging. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-ADM-007 | Admin system/infrastructure/backup | Admin checks health/runtime/docker/log/backup/restore APIs. | System endpoints return expected status or controlled error. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## AI Chatbot
Feature | AI Chatbot
Test requirement | Validate AI conversation, messages, read/write tools, action confirmation/rejection, and unavailable-provider behavior.
Number of TCs | 5
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 0 | 0 | 5 | 0
Round 2 | 0 | 0 | 0 | 5
Round 3 | 0 | 0 | 0 | 5
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
TR-AI-001 | Create AI conversation | Member creates a family-scoped AI conversation. | Conversation is created under current family/member. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-AI-002 | Send normal AI message | Send message that does not require action. | User and AI messages are stored; related module is inferred. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-AI-003 | Use read tool answer | Ask finance/task/calendar question that requires read tool. | Tool is executed and final answer uses returned context. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-AI-004 | Confirm write action | AI proposes write action, user confirms. | Pending action changes to CONFIRMED and underlying service executes once. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
TR-AI-005 | Reject or expire action / provider missing | Reject/expire pending action or run with missing OpenAI API key. | Action is not executed; system returns controlled status/error. | FE build, backend API, database seed, and required mocked/test-mode external services are available. | Pending |  |  | N/A |  |  | N/A |  |  | Pending until FE/system integration environment is available.
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case